## Objectives-2025
SN | Department | Objective | Objective Status | Objective start date | Objective end date /expected | Monitoring Methodology *Pareto - Measuring the objective in cumulative percentage | Monitoring Frequency *Daily *Weekly *Fortnightly *Monthly *Quarterly *Half Yearly *Yearly | Percentage Completion | Objective Achievement Plans |  |  | Responsibility
[9 empty] | Steps | Percentage level | Status
1 | Management | To become an approved contractor under TAQA Abu Dhabi Water and Electricity Authority (ADEWA) | Achieved | 2023-01-01 | 2025-03-31 | Pareto Chart | Weekly | 100% | *Submitting primary application *Submitting pre-qualifications *Qualified for Technical verification *Registration completion with final approval | 20% 30% 20% 30% | Completed Completed Completed Completed | Nikki,Ishan and Paul
2 | Sales | To be awarded project RMS Solutions for BTS/Telecom Towers | Under Process | 2024-03-08 | 2025-12-31 | Pareto Chart | Monthly | 50% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Receive the Purchase Order | 10% 20% 20% 20% 30% | Completed Completed Completed Pending Pending | Nikki,Ishan and Vishal
3 | Sales | To be awarded project I059 Al Falah Construction Works - 17074 | Under Process | 2024-04-22 | 2025-12-31 | Pareto Chart | Fortnightly | 70% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Pending Pending | Nikki, Viswanath and Ishan
4 | Sales | To be awarded OMAN - Rooftop Solar Project - 3 MW-17100 | Under Process | 2025-04-21 | 2025-12-31 | Pareto Chart | Weekly | 50% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Pending Pending Pending | Nikki and Paul
5 | Sales | To be awarded 3 Nos. RMU Stations for Solar PV Plant at Al Wathba Farms-17101 | Under Process | 2025-04-06 | 2025-12-31 | Pareto Chart | Weekly | 70% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Pending Pending | Nikki and Paul
6 | Sales | To be awarded D-114000 - RW SCADA and RTU’s Maintenance Contract - TAQA | Under Process | 2025-05-01 | 2025-12-31 | Pareto Chart | Weekly | 30% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Pending Pending Pending Pending | Nikki, Vishal and Ishan
7 | Sales | To be awarded D-113785 - Construction for Integration of Distribution Substation to DMS in Eastern Region lot-1 Bundle-1 | Under Process | 2025-05-01 | 2025-12-31 | Pareto Chart | Weekly | 30% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Pending Pending Pending Pending | Nikki, Vishal and Ishan
8 | Project Management | To complete the Industry 4.0 Project for Somika | Achieved | 2025-01-01 | 2025-04-15 | Pareto Chart | Weekly | 100% | *Project kickoff meeting & documentation of scope *Development of detailed project schedule and resource plan *Weekly progress tracking and risk mitigation planning *Cost control and budget adherence reviews *Client coordination, feedback, and change management documentation *Final project delivery, internal review, and client sign-off | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Completed Completed | Nikki, Vishal and Ishan
9 | Project Management | To complete the Project 17062 - Al Hudayriyat PDA - 15 Nos. RTU | Under Process | 2025-01-01 | 2025-12-31 | Pareto Chart | Weekly | 80% | *Project kickoff meeting & documentation of scope *Development of detailed project schedule and resource plan *Weekly progress tracking and risk mitigation planning *Cost control and budget adherence reviews *Client coordination, feedback, and change management documentation *Final project delivery, internal review, and client sign-off | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Completed Pending | Vishal and Ishan
10 | Project Management | To complete the Project 17062 - Al Hudayriyat Island - 4 Nos. RTU | Under Process | 2025-01-01 | 2025-12-31 | Pareto Chart | Weekly | 80% | *Project kickoff meeting & documentation of scope *Development of detailed project schedule and resource plan *Weekly progress tracking and risk mitigation planning *Cost control and budget adherence reviews *Client coordination, feedback, and change management documentation *Final project delivery, internal review, and client sign-off | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Completed Pending | Vishal and Ishan
11 | Project Management | To complete the Project 17063 - Al Hudayriyat HPDA - 4 Nos. RTU | Under Process | 2025-01-01 | 2025-12-31 | Pareto Chart | Weekly | 80% | *Project kickoff meeting & documentation of scope *Development of detailed project schedule and resource plan *Weekly progress tracking and risk mitigation planning *Cost control and budget adherence reviews *Client coordination, feedback, and change management documentation *Final project delivery, internal review, and client sign-off | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Completed Pending | Vishal and Ishan
12 | Project Management | To complete the Project 17073 - Al Hudayriyat Dome - 1 No. RTU | Under Process | 2025-01-01 | 2025-12-31 | Pareto Chart | Weekly | 80% | *Project kickoff meeting & documentation of scope *Development of detailed project schedule and resource plan *Weekly progress tracking and risk mitigation planning *Cost control and budget adherence reviews *Client coordination, feedback, and change management documentation *Final project delivery, internal review, and client sign-off | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Completed Pending | Vishal and Ishan
13 | Sales | To Secure Industry 4.0 Project with Nestle | Under Process | 2025-05-01 | 2025-12-31 | Pareto Chart | Weekly | 10% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Pending Pending Pending Pending Pending | Nikki and Ishan

## Objectives-2026
SN | Department | Objective | Objective Status | Objective start date | Objective end date /expected | Monitoring Methodology *Pareto - Measuring the objective in cumulative percentage | Monitoring Frequency *Daily *Weekly *Fortnightly *Monthly *Quarterly *Half Yearly *Yearly | Percentage Completion | Objective Achievement Plans |  |  | Responsibility
[9 empty] | Steps | Percentage level | Status
1 | Management | To become an approved DISTRIBUTION PRIMARY SUBSTATION contractor under TAQA | Under Process | 2026-01-01 | 2026-08-31 | Pareto Chart | Weekly | 50% | *Submitting primary application *Submitting pre-qualifications *Qualified for Technical verification *Registration completion with final approval | 20% 30% 20% 30% | Completed Completed Pending Pending | Nikki and Paul
2 | Sales | To be awarded ENEC Tender 0950-D E642-001 for upgtade of electrical network & distribution substations at Barakah site - 17144 | Under Process | 05.05.2026 | 2026-12-31 | Pareto Chart | Monthly | 30% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Pending Pending Pending Pending | Nikki,Paul, Sherin and Vishal
3 | Sales | To be awarded Supply of MOXA Ethernet Switch MOXA EDS-4008-2GT-2GS-LV-T for the DMS-RTU Panel - 17141 | Under Process | 22.04.2025 | 2026-12-31 | Pareto Chart | Monthly | 60% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Pending Pending | Nikki,Paul, Sherin and Vishal
4 | Sales | To be awarded D-115023 - 26-33. D-115023. 33kV & 11kV PU for ALADLA Farms (RTU-Telecom-ADMS) - 17140 | Under Process | 2024-03-08 | 2026-12-31 | Pareto Chart | Monthly | 60% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Pending Pending | Nikki,Paul, Sherin and Vishal
5 | Sales | To be awarded Project EPE Consultancy - 17127 | Achieved | 01.04.2026 | 2026-12-31 | Pareto Chart | Weekly | 100% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Completed Completed | Nikki,Paul, Sherin and Vishal
6 | Sales | To be awarded 241503 - RA4108 - Gardenia, Yas Island - 17126 | Under Process | 2026-03-30 | 2026-12-31 | Pareto Chart | Fortnightly | 60% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Pending Pending | Nikki,Paul, Sherin and Vishal
7 | Sales | To be awarded D-114063~Construction works for Integration of Distribution Substation to DMS in Eastern Region - 17105 | Under Process | 2025-08-08 | 2025-12-31 | Pareto Chart | Weekly | 30% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Pending Pending | Nikki,Paul, Sherin and Vishal
8 | Sales | To be awarded - I072- Phase 2 Reem Hills - 7 Substations (240654) - 17090 | Under Process | 2025-08-01 | 2026-12-31 | Pareto Chart | Weekly | 60% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Pending Pending | Nikki,Paul, Sherin and Vishal
9 | Sales | To be awarded I066 - BALGHAIYLAM VILLAS AND INFRASTRUCTURE (32 Stations) - 17079 | Under Process | 2025-06-01 | 2026-12-31 | Pareto Chart | Weekly | 100% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Completed Completed | Nikki,Paul, Sherin and Vishal
10 | Sales | To be awarded - I057 CONSTRUCTION OF UTILITIES WORK ASSOSIATED ADDC – RTU for 5 system (Trojan Tender No 145330”) - 17071 | Under Process | 2025-06-01 | 2026-12-31 | Pareto Chart | Weekly | 60% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Pending Pending | Nikki,Paul, Sherin and Vishal
11 | Sales | To be awarded OMAN - Rooftop Solar Project - 3 MW-17100 | Under Process | 2025-04-21 | 2026-12-31 | Pareto Chart | Weekly | 60% | *Fix meetings to promote our services *Receive RFQ from clients *Submit the Technical proposal *Submit the Commercial proposal *Meeting to discuss the proposed solution *Receive the Purchase Order | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Pending Pending | Nikki,Paul, Sherin and Vishal
12 | Project Management | To complete the Project 17062 - Al Hudayriyat PDA - 15 Nos. RTU | Under Process | 2025-01-01 | 2026-12-31 | Pareto Chart | Weekly | 80% | *Project kickoff meeting & documentation of scope *Development of detailed project schedule and resource plan *Weekly progress tracking and risk mitigation planning *Cost control and budget adherence reviews *Client coordination, feedback, and change management documentation *Final project delivery, internal review, and client sign-off | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Completed Pending | Vishal and Sherin
13 | Project Management | To complete the Project EPE consultancy - 17127 | Under Process | 2026-04-01 | 2026-12-31 | Pareto Chart | Weekly | 80% | *Project kickoff meeting & documentation of scope *Development of detailed project schedule and resource plan *Weekly progress tracking and risk mitigation planning *Cost control and budget adherence reviews *Client coordination, feedback, and change management documentation *Final project delivery, internal review, and client sign-off | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Completed Completed Pending | Vishal and Sherin
14 | Project Management | To complete the Project I066 - BALGHAIYLAM VILLAS AND INFRASTRUCTURE -32 Stations - (NPC 234707) - 17079 | Under Process |  |  | Pareto Chart | Weekly | 50% | *Project kickoff meeting & documentation of scope *Development of detailed project schedule and resource plan *Weekly progress tracking and risk mitigation planning *Cost control and budget adherence reviews *Client coordination, feedback, and change management documentation *Final project delivery, internal review, and client sign-off | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Pending Pending Pending | Vishal and Sherin
15 | Project Management | To completed the Prjoect I057 CONSTRUCTION OF UTILITIES WORK ASSOSIATED ADDC – RTU for 5 system (Trojan Tender No 145330”) - 17071 | Under Process |  |  | Pareto Chart | Weekly | 50% | *Project kickoff meeting & documentation of scope *Development of detailed project schedule and resource plan *Weekly progress tracking and risk mitigation planning *Cost control and budget adherence reviews *Client coordination, feedback, and change management documentation *Final project delivery, internal review, and client sign-off | 10% 20% 20% 20% 10% 20% | Completed Completed Completed Pending Pending Pending | Vishal and Sherin